# Hackathon Logistics Coordination Meeting - Conversation

# Transcript

U. Anand Williams: Good morning, Dr. Smith and Prof. Davis. Thank you for taking the time to meet today to finalise the extended logistics for the upcoming CSE and ACSE Interdepartmental Hackathon.

Dr Smith (HOD): Good morning, Anand. I'm glad we could get together. I see the proposal was officially approved for October 18th. We have a lot of ground to cover to ensure this runs smoothly for the 100 to 150 students we expect.

Prof. Davis (N-Block Admin): Morning, both. Let’s start with the venue. Room N-308 is reserved. I’ve extended your access window. You can get in at 8:00 AM on the 18th for setup. The event kicks off at 10:00 AM, which gives your team two solid hours.

U. Anand Williams: That’s a huge help, Prof. Davis. For the seating arrangement, we’d like to organise the desks into clusters of four to facilitate teamwork. Is the custodial staff available to help us rearrange the room?

Prof. Davis: Yes, I will submit a work order for the custodial team to arrange the clusters the night before. You won't have to do heavy lifting on the morning of the event.

U. Anand Williams: Excellent. Regarding IT infrastructure—we are expecting around 120 to 150 students, which means over 100 laptops connecting simultaneously. Will the standard Wi-Fi handle that without dropping?

Prof. Davis: The bandwidth in N-Block is robust, but to be safe, I am going to have the IT department spin up a dedicated temporary SSID just for the hackathon participants. It will prevent any interference with standard campus traffic. However, we will definitely need power extension boards for every table cluster.

U. Anand Williams: I will submit the formal IT request ticket for the extension boards by this Friday. Now, moving on to the themes and tracks. We want the problem statements to be highly relevant. We're considering tracks on 'Smart Campus Solutions', 'AI in Education', and 'Sustainable Tech'.

Dr. Smith: Those are excellent, forward-thinking tracks. I especially like the Smart Campus theme. It gives students a chance to solve localised problems. What are you planning for the prizes?

U. Anand Williams: We are looking into providing one-year IEEE student memberships for the winning team, along with department certificates of excellence. For the runner-ups, we might distribute some tech peripherals. Do we have department budget approval for the IEEE memberships?

Dr Smith: Yes, I can approve the budget for the IEEE memberships. It aligns perfectly with our goal to increase professional organisational engagement among students. Just send me the invoice once finalised.

U. Anand Williams: Thank you, sir. That will be a great incentive for the participants. Next on the agenda is catering. We have a 4-hour active coding window. I was thinking of providing boxed lunches around 12:30 PM to minimise disruption.

Prof. Davis: Boxed lunches are the best option for N-308. We don't want a buffet line causing a mess near the workstations. I’ll ensure extra trash receptacles are placed in the room. Just make sure students keep food away from the extension boards.

U. Anand Williams: Noted. We will enforce a strict 'drinks with lids only' rule near the hardware. What about the evaluation phase? The coding stops at 2:00 PM, and judging begins at 3:00 PM.

Dr Smith: I’ve spoken to Dr Lee and Prof. Sharma. They are confirmed as your primary judges. They have both mentored capstone projects, so they know exactly what to look for.

U. Anand Williams: Perfect. I’m currently finalising the evaluation rubrics. The scoring will be heavily weighted on innovation, practical execution, and code quality. Some students are integrating databases and Python backend systems, so the technical evaluation needs to be thorough.

Dr Smith: Make sure you send that rubric to Dr Lee and Prof. Sharma by next Tuesday. They need time to review the criteria. Also, will you need a microphone or PA system for the opening and closing remarks?

Prof. Davis: There is a standard podium and mic setup in N-308, but I will ask IT to double-check the battery packs and audio levels when they set up the dedicated Wi-Fi.

U. Anand Williams: That covers everything on my list. To summarise: I’ll submit the IT ticket for power boards, finalise the rubrics for the judges, and send the budget request for the IEEE membership prizes. Thank you both for your guidance and support.

Dr. Smith: You're welcome, Anand. It sounds like you have a solid plan. Keep us updated on the registration numbers as we get closer to the date.

# Meeting Notes: Hackathon Logistics Coordination

Date: October 4, 2026

Attendees: U. Anand Williams (Organiser), Dr Smith (HOD), Prof. Davis (N-Block Admin)

Objective: Finalise venue readiness, technical requirements, catering, and evaluation faculty for the CSE & ACSE Interdepartmental Hackathon.

## Key Discussions

Venue Setup: Room N-308 is secured. Organisers are granted early access at 8:00 AM on October 18 for setup. Custodial staff will pre-arrange desks into clusters of four.

IT & Infrastructure: IT will create a dedicated temporary SSID for the hackathon to handle the 120+ laptops. Power extension boards are required for all clusters.

Themes & Prizes: The hackathon will feature tracks on Smart Campus Solutions, AI in Education, and Sustainable Tech. The winning team will receive IEEE student memberships, funded by the department budget.

Catering: Boxed lunches will be provided at 12:30 PM to minimise disruption. Extra trash receptacles will be provided, and strict food/drink rules will be enforced near hardware.

Evaluations: Dr Lee and Prof. Sharma are confirmed as judges for the 3:00 PM evaluation phase. Judging criteria will focus on innovation, execution, and code quality.

## Action Items

U. Anand Williams: Submit a formal IT request ticket for power extension boards by Friday, October 9.

U. Anand Williams: Finalise and email the project evaluation rubrics to Dr Lee and Prof. Sharma by Tuesday, October 6.

U. Anand Williams: Submit the formal invoice/budget request to Dr Smith for the IEEE membership prizes.

Prof. Davis: Coordinate with custodial staff for room layout and IT for the dedicated SSID and PA system check.